## Dashboard
XYTheta Pen Plotter Project Dashboard
Schedule baseline: 2026-06-01 through 2026-12-29. Change dates and statuses on the Gantt sheet.
TOTAL TASKS |  |  | COMPLETE | IN PROGRESS | BLOCKED
49 |  |  | 1 | 0 | 0
Phase | Tasks | Complete | Average Progress
Phase 0 - Repository | 1 | 1 | 100%
Phase 1 - Electrical | 12 | 0 | 0%
Phase 2 - Controller | 6 | 0 | 0%
Phase 3 - Single Axis | 5 | 0 | 0%
Phase 4 - Three Axis | 6 | 0 | 0%
Phase 5 - Toolhead | 8 | 0 | 0%
Phase 6 - Integration | 5 | 0 | 0%
Phase 7 - Validation | 6 | 0 | 0%
Current Focus
Complete the Phase 1 bench worksheet before connecting motors or the toolhead to RP23CNC. Record evidence in lab notes, then update ROADMAP.md and this workbook together.
Status Legend
Not Started | In Progress | Blocked | Complete

## Gantt
Theta Pen Plotter Project Gantt
Editable schedule generated from docs/project/ROADMAP.md. Update task inputs, then keep roadmap evidence/checklists authoritative.
Edit columns D-H, J-M. End dates and summaries are formula-driven. Timeline bars update from Start, End, and Status.
ID | Phase | Task | Owner | Status | Priority | Duration | Start | End | Progress | Predecessor | Evidence / Exit Proof | Notes | 2026-06-01 17:00 | 2026-06-08 17:00 | 2026-06-15 17:00 | 2026-06-22 17:00 | 2026-06-29 17:00 | 2026-07-06 17:00 | 2026-07-13 17:00 | 2026-07-20 17:00 | 2026-07-27 17:00 | 2026-08-03 17:00 | 2026-08-10 17:00 | 2026-08-17 17:00 | 2026-08-24 17:00 | 2026-08-31 17:00 | 2026-09-07 17:00 | 2026-09-14 17:00 | 2026-09-21 17:00 | 2026-09-28 17:00 | 2026-10-05 17:00 | 2026-10-12 17:00 | 2026-10-19 17:00 | 2026-10-26 17:00 | 2026-11-02 18:00 | 2026-11-09 18:00 | 2026-11-16 18:00 | 2026-11-23 18:00 | 2026-11-30 18:00 | 2026-12-07 18:00 | 2026-12-14 18:00 | 2026-12-21 18:00 | 2026-12-28 18:00
P0-01 | Phase 0 - Repository | Repository organization and documentation baseline | Codex | Complete | High | 5 | 2026-06-01 17:00 | 2026-06-05 17:00 | 100% |  | ROADMAP Phase 0 | Completed before hardware bring-up
P1-01 | Phase 1 - Electrical | Inventory and photograph RP23CNC kits and PCB revision (E-16) | Project Owner | Not Started | High | 2 | 2026-06-15 17:00 | 2026-06-16 17:00 | 0% |  | Photo + E-16 lab note
P1-02 | Phase 1 - Electrical | Solder and inspect RP23CNC connectors and Ethernet components (E-17) | Project Owner | Not Started | High | 4 | 2026-06-17 17:00 | 2026-06-20 17:00 | 0% | P1-01 | Photos + continuity results
P1-03 | Phase 1 - Electrical | Identify driver, sensor, and module revisions | Project Owner | Not Started | Medium | 2 | 2026-06-17 17:00 | 2026-06-18 17:00 | 0% | P1-01 | Component photos
P1-04 | Phase 1 - Electrical | Verify S-120-12 labels, earth continuity, and no-load output (E-11) | Project Owner | Not Started | High | 2 | 2026-06-22 17:00 | 2026-06-23 17:00 | 0% | P1-02 | E-11 lab note
P1-05 | Phase 1 - Electrical | Measure stepper coil pairs and resistance (E-01) | Project Owner | Not Started | High | 1 | 2026-06-24 17:00 | 2026-06-24 17:00 | 0% | P1-04 | E-01 results
P1-06 | Phase 1 - Electrical | Document TB6600 switches and verify STEP/DIR behavior (E-02/E-03) | Project Owner | Not Started | High | 3 | 2026-06-25 17:00 | 2026-06-27 17:00 | 0% | P1-05 | E-02/E-03 results
P1-07 | Phase 1 - Electrical | Characterize N20 actuator current (E-05/E-06) | Project Owner | Not Started | High | 2 | 2026-06-29 17:00 | 2026-06-30 17:00 | 0% | P1-04 | E-05/E-06 results
P1-08 | Phase 1 - Electrical | Calibrate load cell and characterize HX711 rate/noise (E-07/E-08) | Project Owner | Not Started | High | 4 | 2026-07-01 17:00 | 2026-07-04 17:00 | 0% | P1-07 | Calibration data
P1-09 | Phase 1 - Electrical | Verify TMAG5273 readings and geometry (E-09) | Project Owner | Not Started | Medium | 2 | 2026-07-06 17:00 | 2026-07-07 17:00 | 0% | P1-08 | E-09 results
P1-10 | Phase 1 - Electrical | Configure and load-test 6 V buck converter (E-14/E-15) | Project Owner | Not Started | High | 3 | 2026-07-08 17:00 | 2026-07-10 17:00 | 0% | P1-07 | E-14/E-15 results
P1-11 | Phase 1 - Electrical | Complete power budget, fuses, wire gauges, and wiring evidence | Project Owner | Not Started | High | 4 | 2026-07-13 17:00 | 2026-07-16 17:00 | 0% | P1-04,P1-10 | BOM + wiring table
P1-GATE | Phase 1 - Electrical | Milestone: electrical characterization gate | Project Owner | Not Started | High | 1 | 2026-07-17 17:00 | 2026-07-17 17:00 | 0% | P1-11 | Phase 1 checklist | All compatibility gates resolved
P2-01 | Phase 2 - Controller | Build or obtain RP23CNC-compatible grblHAL firmware | Codex | Not Started | High | 5 | 2026-07-20 17:00 | 2026-07-24 17:00 | 0% | P1-GATE | Build record
P2-02 | Phase 2 - Controller | Archive source commits, board target, plugins, and options | Codex | Not Started | Medium | 2 | 2026-07-23 17:00 | 2026-07-24 17:00 | 0% | P2-01 | Firmware README
P2-03 | Phase 2 - Controller | Flash board and verify USB/Ethernet communication (F-01) | Project Owner | Not Started | High | 3 | 2026-07-27 17:00 | 2026-07-29 17:00 | 0% | P2-01 | F-01 result
P2-04 | Phase 2 - Controller | Verify converter parser subset and unpowered STEP/DIR (F-02/F-03) | Project Owner | Not Started | High | 3 | 2026-07-30 17:00 | 2026-08-01 17:00 | 0% | P2-03 | F-02/F-03 results
P2-05 | Phase 2 - Controller | Verify limit inputs, M3/M5 output, and settings persistence (F-04/F-05/F-06) | Project Owner | Not Started | High | 4 | 2026-08-03 17:00 | 2026-08-06 17:00 | 0% | P2-04 | F-04 to F-06 results
P2-GATE | Phase 2 - Controller | Milestone: controller baseline gate | Project Owner | Not Started | High | 1 | 2026-08-07 17:00 | 2026-08-07 17:00 | 0% | P2-05 | Phase 2 checklist
P3-01 | Phase 3 - Single Axis | Configure one TB6600 and connect motor without mechanics | Project Owner | Not Started | High | 2 | 2026-08-10 17:00 | 2026-08-11 17:00 | 0% | P2-GATE | Configuration record
P3-02 | Phase 3 - Single Axis | Complete low-speed jog and temperature test (M-01) | Project Owner | Not Started | High | 2 | 2026-08-12 17:00 | 2026-08-13 17:00 | 0% | P3-01 | M-01 result
P3-03 | Phase 3 - Single Axis | Ramp rate/acceleration and set conservative margin (M-02) | Project Owner | Not Started | High | 3 | 2026-08-14 17:00 | 2026-08-16 17:00 | 0% | P3-02 | M-02 result
P3-04 | Phase 3 - Single Axis | Install and verify home/limit switch | Project Owner | Not Started | Medium | 2 | 2026-08-19 17:00 | 2026-08-20 17:00 | 0% | P3-03 | Switch test
P3-GATE | Phase 3 - Single Axis | Milestone: single-axis motion gate | Project Owner | Not Started | High | 1 | 2026-08-21 17:00 | 2026-08-21 17:00 | 0% | P3-04 | Phase 3 checklist
P4-01 | Phase 4 - Three Axis | Bring up X, Y, and A motors and drivers | Project Owner | Not Started | High | 4 | 2026-08-24 17:00 | 2026-08-27 17:00 | 0% | P3-GATE | Bring-up notes
P4-02 | Phase 4 - Three Axis | Calibrate X/Y steps per mm and A motor degrees (M-03/M-04) | Project Owner | Not Started | High | 4 | 2026-08-28 17:00 | 2026-08-31 17:00 | 0% | P4-01 | M-03/M-04 results
P4-03 | Phase 4 - Three Axis | Verify 12:1 bed ratio and tune rates/acceleration (M-05) | Project Owner | Not Started | High | 3 | 2026-09-03 17:00 | 2026-09-05 17:00 | 0% | P4-02 | M-05 result
P4-04 | Phase 4 - Three Axis | Add homing and soft limits (M-07) | Project Owner | Not Started | High | 3 | 2026-09-08 17:00 | 2026-09-10 17:00 | 0% | P4-03 | M-07 result
P4-05 | Phase 4 - Three Axis | Run coordinated tests and converter sample without tool (M-06) | Project Owner | Not Started | High | 4 | 2026-09-11 17:00 | 2026-09-14 17:00 | 0% | P4-04 | M-06 result + G-code
P4-GATE | Phase 4 - Three Axis | Milestone: three-axis motion gate | Project Owner | Not Started | High | 1 | 2026-09-17 17:00 | 2026-09-17 17:00 | 0% | P4-05 | Phase 4 checklist
P5-01 | Phase 5 - Toolhead | Finalize toolhead controller placement | Project Owner | Not Started | High | 3 | 2026-09-21 17:00 | 2026-09-23 17:00 | 0% | P1-GATE | ADR update
P5-02 | Phase 5 - Toolhead | Verify actuator direction and safe travel (T-01) | Project Owner | Not Started | High | 3 | 2026-09-24 17:00 | 2026-09-26 17:00 | 0% | P5-01 | T-01 result
P5-03 | Phase 5 - Toolhead | Implement BOOT/LIFT/SEEK/HOLD/FAULT state machine | Codex | Not Started | High | 8 | 2026-09-28 17:00 | 2026-10-05 17:00 | 0% | P5-02 | Firmware commit
P5-04 | Phase 5 - Toolhead | Add travel, timeout, sensor, and force-limit faults | Codex | Not Started | High | 4 | 2026-10-06 17:00 | 2026-10-09 17:00 | 0% | P5-03 | Firmware tests
P5-05 | Phase 5 - Toolhead | Characterize backlash and implement contact seek (T-02) | Project Owner | Not Started | High | 4 | 2026-10-12 17:00 | 2026-10-15 17:00 | 0% | P5-04 | T-02 result
P5-06 | Phase 5 - Toolhead | Implement and tune force control (T-03) | Codex | Not Started | High | 7 | 2026-10-16 17:00 | 2026-10-22 17:00 | 0% | P5-05 | T-03 data + firmware
P5-07 | Phase 5 - Toolhead | Verify missing-paper, overforce, and disconnect faults (T-04 to T-06) | Project Owner | Not Started | High | 4 | 2026-10-26 17:00 | 2026-10-29 17:00 | 0% | P5-06 | T-04 to T-06 results
P5-GATE | Phase 5 - Toolhead | Milestone: toolhead bench-loop gate | Project Owner | Not Started | High | 1 | 2026-10-30 17:00 | 2026-10-30 17:00 | 0% | P5-07 | Phase 5 checklist
P6-01 | Phase 6 - Integration | Connect grblHAL M3/M5 to toolhead ENGAGE/LIFT | Project Owner | Not Started | High | 3 | 2026-11-02 18:00 | 2026-11-04 18:00 | 0% | P4-GATE,P5-GATE | Interface test
P6-02 | Phase 6 - Integration | Verify reset/E-stop safety and G4 dwell timing | Project Owner | Not Started | High | 3 | 2026-11-05 18:00 | 2026-11-07 18:00 | 0% | P6-01 | Safety test
P6-03 | Phase 6 - Integration | Check toolhead workload for lost steps or jitter | Project Owner | Not Started | High | 3 | 2026-11-10 18:00 | 2026-11-12 18:00 | 0% | P6-02 | Timing measurements
P6-04 | Phase 6 - Integration | Complete calibration and theta-heavy drawings | Project Owner | Not Started | High | 5 | 2026-11-13 18:00 | 2026-11-17 18:00 | 0% | P6-03 | Drawings + photos
P6-GATE | Phase 6 - Integration | Milestone: system integration gate | Project Owner | Not Started | High | 1 | 2026-11-20 18:00 | 2026-11-20 18:00 | 0% | P6-04 | Phase 6 checklist
P7-01 | Phase 7 - Validation | Measure calibration-pattern dimensions and execution time | Project Owner | Not Started | High | 4 | 2026-11-23 18:00 | 2026-11-26 18:00 | 0% | P6-GATE | Measurement tables
P7-02 | Phase 7 - Validation | Record force error during straight, curved, and rotating moves | Project Owner | Not Started | High | 4 | 2026-11-30 18:00 | 2026-12-03 18:00 | 0% | P7-01 | Force plots
P7-03 | Phase 7 - Validation | Photograph final wiring/mechanics and archive firmware/settings | Project Owner | Not Started | Medium | 3 | 2026-12-04 18:00 | 2026-12-06 18:00 | 0% | P7-02 | Photos + build archive
P7-04 | Phase 7 - Validation | Document results, failures, limitations, and future work | Codex | Not Started | High | 6 | 2026-12-09 18:00 | 2026-12-14 18:00 | 0% | P7-03 | Report draft
P7-05 | Phase 7 - Validation | Complete and export Systems Integration report | Codex | Not Started | High | 8 | 2026-12-17 18:00 | 2026-12-24 18:00 | 0% | P7-04 | Final report
P7-GATE | Phase 7 - Validation | Milestone: project validation and report complete | Project Owner | Not Started | High | 1 | 2026-12-29 18:00 | 2026-12-29 18:00 | 0% | P7-05 | Phase 7 checklist

## Lists
Status | Priority | Owner
Not Started | High | Project Owner
In Progress | Medium | Codex
Blocked | Low | Shared
Complete